## Sheet1
Task# | Task | Duration | Resource | Dependency
1 | Build retaining wall | 5 | Landscaper
2 | Level grassed area | 1 | Landscaper | 1
3 | Level paving areas | 1 | Landscaper | 2
4 | Lay paving/concrete | 2 | Concreter | 3
5 | Add top soil | 1 | John | 4
6 | Roll out grass | 1 | Grass expert | 5
7 | Build veggie patch containers | 1 | Landscaper | 6
8 | Set veggie patch containers in place | 1 | Landscaper | 7
9 | Add soil to veggie patch containers | 1 | Landscaper | 8
10 | Plant veggies | 1 | John | 9
11 | Build verandah | 6 | Verandah expert | 10