## Sheet1
Task Description |  | Duration
Project Planning
| Write proposal for idea in a few hundred words, outlining the opportunity, solution and some of the needs | 1
| Learn how to create Gantt charts and why they are useful | 1
| Do example Gantt chart based on backyard project | 1
| Create Gannt Chart | 1
| Create Blog for Ideas | 1
| Have project plan finished | -
Data Collection
| Ask maths club team what features we would like | 1
| talk to mr mccarty and ask him what he thinks would be needed | 1
| send a survey out to maths club students and ask them what they like about the current system and what they don't | 2
| make observations of the current system's pros and cons | 1
| write document with all data as summary | 2
| have data collection phase finished | -
SRS (Software Requirements Specifications)
| Outline the scope of the solution and write down what the solution will have in it | 1
| Outline all constraints and document them with the scope | 1
| Outline what stack will be used and what each component will do in the stack | 1
| Complete an SRS document including requirements and analysis of the software solution | 2
| have SRS document finished | -
Create Designs + Ideas
| Mindmap design ideas and different variations | 1
| Create first design wireframe in Figma for the app and software solution | 3
| Ask others for feedback on your first design (family, friends, maths club students + peers) | 1
| Create second alternative design wireframe for the app in Figma | 3
| Create GUI mockup, with data dictionaries and pseudocode designs for complex functions | 3
| Have initial mockup and design finished | -
| Get feedback on GUI mockup and then document analysis of design | 2
Develop Solution
| Complete Development | 10
Evaluate Solution
| Complete Evaluation | 10